## Login
Project name | Nictus Consultant
Module Name | Sign up/Login
Create By | M. Uzair
Date of Creation | 21/6/2022
Sub Module | Sign Up as a User
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
S-1 | Sign up as user | Sign up | 1-Go to login page | alex@gmail.com 12345678 | Sign Up success | Successfully Sign up | Pass
2-then click as a user
3-Enter details
4-Go to login page
New user are successfully added but need to apply restrication on email varification |  |  | 5-then Click "Submit"button
Sub Module | Sign Up as a Consultant
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
S-2 | Sign up as a consultant | Sign up | 1-Go to login page | bary@gmail.com bary1234 | Sign Up success | Successfully Sign up | Pass
2-then click as a Consultant
3-Enter details
4-Go to login page
5-then Click "Submit"button
New Consultant are successfully added but need to apply restrication on email varification
Sub Module | Login as User
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
L-1 | Login as a User | Login | 1-Go to login page | alex@gmail.com 12345678 | Login success | Successfully login | Pass
2-then click As a User
3-Enter Email
4-Enter Password
5-then Click "Submit"button
New User are successfully Login
Sub Module | Login as a Consultant
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
L-2 | Login as Consultant | Login | 1-Go to login page | bary@gmail.com bary1234 | Login success | Successfully login | Pass
2-then click As a User
3-Enter Email
4-Enter Password
5-then Click "Submit"button
New Consultant are successfully login
Sub Module | Login as Admin
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
A-1 | Login as Admin | Admin Login | 1-Go to browser | admin@gmail.com ******** | Login Success | Successfully Login as admin | Pass
2-Enter web url with admin/login
3- https://demo.consultant.nictusthemes.com/admin/login
4-then enter the email
5-then enter the password
6-then Click "Login "button

## consultant category
Project name | Consultant
Module Name | Consultant Category
Create By | M. Uzair
Date of Creation | 23/6/2022
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail) | on Add new
1 | Consultant Category List | Add new Category | 1-Go to admin pannel | GYM | Should Successful Create New Consultant | Successfully Created | Pass | 1-Name is require
|  |  | 2-Click on consultant category |  |  |  |  | 2-On edit name
|  |  | 3-Click on add new |  |  |  |  | 3- On submission
4-Enter details
5-Click on submit button
2 | Consultant Category List | Edit Category | 1-Go to admin pannel | GYM | Should Successful Edit Consultant | Successfully Update the Consultant | Pass
2-Click on consultant category
3-Select category name
4-click on action button
5-Edit details
6-Click on update button
3 | Consultant Category List | Delete Category | 1-Go to admin pannel | GYM | Should Successful Deleted Consultant | Successfully delete | Pass
2-Click on consultant category
3-Select category name
4-click on delete icon
Note on I9: Dell: not add with same name
Note on I10: Dell: when we add in mentor only name it can create new catagory

## pending consultant
Project name | Consultant
Module Name | Pending Consultant
Create By | M. Uzair
Date of Creation | 23/6/2022
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Pending Consultant | Approve new Consultant | 1-Go to admin pannel | Approve | Should Successful approve | Successfully approved | Pass | when we accept the consultant it goes into approved consultant
2-Click on pending consultant
3-Click on edit icon
4-Enter details
5-Click on submit
2 | Pending Consultant | Edit new Consultant | 1-Go to admin pannel | Reject | Should Successful rejected | Successfully rejected | Pass
2-Click on pending consultant
3-Click on edit icon
4-Enter details
5-Click on submit
Sub Module | Feature Consultant
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant | Feature Consultant | 1-Go to admin Pannel | Edit Consultant | Should update Consultant | Successfully update Consultant | Pass
2-then click on pending consultant
3-Choose yes or no
4-then click on update button
Sub Module | Personal Info
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant personal info | Personal Info | 1-Go to admin Pannel | Edit Consultant | Should update Consultant | Successfully update Consultant | Pass
2-then click on pending consultant
3-edit information
4-then click on update button
Sub Module | Skills
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Skills | Update Skills | 1-Go to admin Pannel | GYM | Should update Consultant | Successfully update Consultant Skills | Pass
2-then click on pending consultant
3-edit skills
4-then click on update button
Sub Module | Bank Account
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Bank account details | Update Bank | 1-Go to admin Pannel | John/ world's bank | Should update Consultant | Successfully update Consultant Bank | Pass
2-then click on pending consultant
3-edit Bank
4-then click on update button
Sub Module | Education
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Education | Update Education | 1-Go to admin Pannel | BBA/2012 | Should update Consultant | Successfully update Consultant Education | Pass
2-then click on pending consultant
3-edit education
4-then click on update button
Sub Module | Experience
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Experience | Update Experience | 1-Go to admin Pannel | AA company | Should update Consultant | Successfully update Consultant Experience | Pass
2-then click on pending consultant
3-edit experience
4-then click on update button

## Aapproved consultant
Project name | Consultant
Module Name | Approved Consultant
Create By | M. Uzair
Date of Creation | 23/6/2022
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Approved Consultant | Edit new Consultant | 1-Go to admin pannel | John John | Should Successful approve | Successfully approved | Pass
2-Click on Approved consultant
3-Click on edit icon
4-Enter details
5-Click on submit
2 | Approved Consultant | Edit new Consultant | 1-Go to admin pannel | John John | Should Successful rejected | Successfully rejected | Pass
2-Click on Approved consultant
3-Click on Action button
4-Enter details
5-Click on submit
3 | Approved Consultant | Delete Consultant | 1-Go to admin pannel | aaaaaaa | Should Successful deleted Consultant | Successfully delete | Pass
2-Click on consultant User
3-Select category name
4-click on delete icon
Sub Module | Feature Consultant
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Feature | Feature Consultant | 1-Go to admin Pannel | John John | Should update Consultant | Successfully update Consultant | Pass
2-then click on pending consultant
3-Choose yes
4-then click on update button
Sub Module | Feature Consultant
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Feature | Feature Consultant | 1-Go to admin Pannel | John John | Should update Consultant | Successfully update Consultant | Pass
2-then click on pending consultant
3-Choose no
4-then click on update button
Sub Module | Personal Info
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant personal info | Personal Info | 1-Go to admin Pannel | Edit Consultant | Should update Consultant | Successfully update Consultant | Pass
2-then click on pending consultant
3-edit information
4-then click on update button
Sub Module | Skills
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Skills | Update Skills | 1-Go to admin Pannel | GYM | Should update Consultant | Successfully update Consultant Skills | Pass
2-then click on pending consultant
3-edit skills
4-then click on update button
Sub Module | Bank Account
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Bank account | Update Bank | 1-Go to admin Pannel | John/ world's bank | Should update Consultant | Successfully update Consultant Bank | Pass
2-then click on pending consultant
3-edit Bank
4-then click on update button
Sub Module | Education
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant education | Update Education | 1-Go to admin Pannel | BBA/2012 | Should update Consultant | Successfully update Consultant Education | Pass
2-then click on pending consultant
3-edit education
4-then click on update button
Sub Module | Experience
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant experience | Update Experience | 1-Go to admin Pannel | AA company | Should update Consultant | Successfully update Consultant Experience | Pass
2-then click on pending consultant
3-edit experience
4-then click on update button

## Rejected consultant
Project name | Consultant
Module Name | Rejected Consultant
Create By | M. Uzair
Date of Creation | 23/6/2022
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Rejected Consultant | Rejected | 1-Go to admin pannel | John john | Should Successful rejected | Successfully Rejected | Pass
2-Click on Rejected consultant
3-Click on action button
4-Click on Approve
When we reject consultant it can show in rejected consultant we can approve again this consultant

## add consultant
Project name | Consultant
Module Name | Add Consultant
Create By | M. Uzair
Date of Creation | 23/6/2022
Sub Module | Personal Info
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant personal info | Personal Info | 1-Go to admin Pannel | Edit Consultant | Should update Consultant | Successfully update Consultant | Pass
2-then click on add consultant
3-edit information
4-then click on update button
Sub Module | Skills
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Skills | Update Skills | 1-Go to admin Pannel | GYM | Should update Consultant | Successfully update Consultant Skills | Pass
2-then click on add consultant
3-edit skills
4-then click on update button
Sub Module | Bank Account
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Bank account | Update Bank | 1-Go to admin Pannel | John/ world's bank | Should update Consultant | Successfully update Consultant Bank | Pass
2-then click on add consultant
3-edit Bank
4-then click on update button

## Add consultant education
Project name | Consultant
Module Name | Add Consultant
Create By | M. Uzair
Date of Creation | 23/6/2022
Sub Module | Education
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Education | Update Education | 1-Go to admin Pannel | John/BBA | Should update Consultant | Successfully Update Consultant Education | Pass
2-then click on add education consultant
3-edit education
4-then click on update button
When we edit Consultant education we select Consultant name
then click on submit button the degree field is required
on submit button it can't show notification update or not

## Add experience
Project name | Consultant
Module Name | Add Consultant
Create By | M. Uzair
Date of Creation | 23/6/2022
Sub Module | Experience
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Edit Consultant Experience | Update Experience | 1-Go to admin Pannel | John/GYM | Should update Consultant | update Consultant Experience | Pass
2-then click on add consultant
3-edit experience
4-then click on submit button
In Consultant Experience when we click on submit button the company field is required
when we enter the company then click the submit button page was reload but it can't show notification what we update

## consultant occupation
Project name | Consultant
Module Name | Consultant Occupation
Create By | M. Uzair
Date of Creation | 23/6/2022
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail) | on Add new
1 | Occupation List | Add new Occupation | 1-Go to admin pannel | Consultant Occupation | Should Successful add occupation | Successfully Created | Pass
2-Click on consultant occupation
3-Click on add new
4-Enter name
5-Click on save changes
2 | Occupation List | Edit Occupation | 1-Go to admin pannel | Consultant Occupation | Should Successful edit occupation | Successfully Updated | Pass
|  |  | 2-Click on consultant occupation |  |  |  |  | In occupation edit only name will change
3-Select occupation name
4-click on edit icon
5-Edit name
6-Click on save changes
3 | Occupation List | Delete Occupation | 1-Go to admin pannel | Consultant Occupation | Should Successful deleted occupation | Successfully delete | Pass
2-Click on consultant occupation
3-Select category name
4-click on delete icon

## consultant degree
Project name | Consultant
Module Name | Consultant Degree
Create By | M. Uzair
Date of Creation | 23/6/2022
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Consultant Degree List | Add new Degree | 1-Go to admin pannel | Gymnastic | Should Successful add Degree | Successfully Created | Pass
2-Click on consultant Degree
3-Click on add new
4-Enter name
5-Click on save changes
2 | Consultant Degree List | Edit Degree | 1-Go to admin pannel | Gymnastics | Should Successful edit Degree | Successfully Update the Consultant | Pass
2-Click on consultant Degree
3-Select Degree name
4-click on action button
5-Edit name
6-Click on save changes
3 | Consultant Degree List | Delete Degree | 1-Go to admin pannel | Gymnastics | Should Successful deleted Degree | Successfully delete | Pass
2-Click on consultant Degree
3-Select category name
4-click on action button

## user list
Project name | Consultant
Module Name | Consultant User
Create By | M. Uzair
Date of Creation | 23/6/2022
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | User List | Add new User | 1-Go to admin pannel | User List | Should Successfully add User | Successfully Created | Pass | Enter wrong country namne its gives error
|  |  | 2-Click on User |  |  |  |  | user created without country name
|  |  | 3-Click on add new |  |  |  |  | when we open user list admin dashboard disappear
4-Enter details
5-Click on submit
2 | User List | Edit User | 1-Go to admin pannel | User List | Should Successful Edit User | Successfully Update the user | Pass
|  |  | 2-Click on User |  |  |  |  | when we edit in user country form gives error
3-Select User name
4-click on edit icon
5-Edit name
6-Click on save changes
3 | User List | Delete User | 1-Go to admin pannel | User List | Should Successfully delete User | Successfully delete | Pass
2-Click on User
3-Select category name
4-click on delete icon

## Newsletter list
Project name | Consultant
Module Name | Newsletter list
Create By | M. Uzair
Date of Creation | 23/6/2022
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Newsletter list | check list | 1-Go to admin pannel | List | Should Successful show email | Successfully Show | Pass
2-Click on newsletter list
3- check the list
4-Email will show in list

## consultant bank
Project name | Consultant
Module Name | Consultant Bank
Create By | M. Uzair
Date of Creation | 23/6/2022
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Consultant Bank List | Add new Bank | 1-Go to admin pannel | World bank | Should Successful add Bank | Successfully Created | Pass
2-Click on consultant Bank
3-Click on add new
4-Enter name
5-Click on save changes
2 | Consultant Bank List | Edit Bank | 1-Go to admin pannel | World's bank | Should Successful edit Bank | Successfully Update the Consultant | Pass
2-Click on consultant Bank
3-Select Bank name
4-click on edit icon
5-Edit name
6-Click on save changes
3 | Consultant Bank List | Delete Bank | 1-Go to admin pannel | World's bank | Should Successful deleted Bank | Successfully delete | Pass
2-Click on consultant Bank
3-Select category name
4-click on delete icon

## appointment log
Project name | Consultant
Module Name | Appointment log
Create By | M. Uzair
Date of Creation | 23/6/2022
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Result | Acutal Result | Status (pass/fail)
1 | Appointment log | check list | 1-Go to admin pannel | check status | Should Successful show email | Successfully Show | Pass
2-Click on Appointment log
3- check the consultant
4-its show table
In appointment log list we select the consultant and click the copy button for copy to clipboard
when we click csv button an exel sheet will download
when we click pdf button the pdf file download
when we click print button the print file will open

## contact us list
Project name | Consultant
Module Name | Contact us list
Create By | M. Uzair
Date of Creation | 23/6/2022
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Result | Acutal Result | Status (pass/fail)
1 | Contact us | check list | 1-Go to admin pannel | check status | Should Successful show message | Successfully Show | Pass
2-Click on contact us list
3-check who wants to contact us
4-Read the message

## withdraw
Project name | Consultant
Module Name | Withdraw request list
Create By | M. Uzair
Date of Creation | 23/6/2022
Sub Module | Paid
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Result | Acutal Result | Status (pass/fail)
1 | Withdraw | check list | 1-Go to admin pannel | check status | Should Sueccessful paid | Already paid | Pass
2-Click on withdraw list
3-check already paid
4-Read the message
Sub Module | Pending
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Result | Acutal Result | Status (pass/fail)
1 | Withdraw | check list | 1-Go to admin pannel | check status | Shouldn't paid | Pay it | Pass
2-Click on withdraw list
3-check pending
4-Read the message

## Blog
Project name | Consultant
Module Name | Blog
Create By | M. Uzair
Date of Creation | 23/6/2022
Sub Module | Blog list
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Blog List | Add new blog | 1-Go to admin pannel | 5th Layer of corona will coming | Should Successful add blog | Successfully Created | Pass
2-Click on blog Posts
3-Click on add new
4-Enter details
5-Click on submit
6-show in blog list
2 | Blog List | Edit blog | 1-Go to admin pannel | 5th Layer of corona will coming | Should Successful edit blog | Successfully Update the blog | Pass
2-Click on blog posts
3-Select name
4-click on action button
5-Edit details
6-Click on submit
3 | Blog List | Delete blog | 1-Go to admin pannel | 5th Layer of corona will coming | Should Successful deleted | Successfully delete | Pass
2-Click on blog list
3-Select category name
4-click on delete icon
Sub Module | Blog Category list
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Resule | Acutal Result | Status (pass/fail)
1 | Blog Category List | Add new blog category | 1-Go to admin pannel | 5th Layer of corona will coming | Should Successful add blog | Successfully Created | Pass
2-Click on blog category list
3-Click on add new
4-Enter details
5-Click on submit
6-show in blog category list
2 | Blog Category List | Edit blog category | 1-Go to admin pannel | 5th Layer of corona will coming | Should Successful edit blog | Successfully Update the blog | Pass
2-Click on blog category list
3-Select name
4-click on action button
5-Edit details
6-Click on submit
3 | Blog Category List | Delete blog category | 1-Go to admin pannel | 5th Layer of corona will coming | Should Successful deleted | Successfully delete | Pass
2-Click on blog category list
3-Select category name
4-click on delete icon

## Payment method
Project name | Consultant
Module Name | Add Payment Method
Create By | M. Uzair
Date of Creation | 23/6/2022
Sub Module | Payment Configuration
Test case ID | Test Module | Test senario | Test Steps | Test data | Expected Result | Acutal Result | Status (pass/fail)
1 | Withdraw | check list | 1-Go to admin pannel | check status | Should Sueccessful paid | Already paid | Pass
2-Click on withdraw list
3-check already paid
4-Read the message
Test Case ID | Test Module | Test Scenario | Test Steps | Test Data | Expected Result | Actual Result | Status (Pass/Fail)
TC_001 | Credit Card Payment | Valid Credit Card Payment | 1. Navigate to payment page. 2. Enter valid credit card details (number, expiration date, CVV). 3. Click on submit. | Valid credit card details | Payment is processed successfully
TC_002 | Credit Card Payment | Invalid Credit Card Number | 1. Navigate to payment page. 2. Enter invalid credit card number. 3. Click on submit. | Invalid credit card number | Error message: "Invalid card number"
TC_003 | Credit Card Payment | Expired Credit Card | 1. Navigate to payment page. 2. Enter expired credit card details. 3. Click on submit. | Expired credit card details | Error message: "Card expired"
TC_004 | Credit Card Payment | Incorrect CVV | 1. Navigate to payment page. 2. Enter valid credit card details with incorrect CVV. 3. Click on submit. | Valid credit card details with incorrect CVV | Error message: "Incorrect CVV"
TC_005 | Credit Card Payment | Missing Expiration Date | 1. Navigate to payment page. 2. Enter credit card details without expiration date. 3. Click on submit. | Credit card details without expiration date | Error message: "Expiration date required"
TC_006 | Debit Card Payment | Valid Debit Card Payment | 1. Navigate to payment page. 2. Enter valid debit card details (number, expiration date, CVV). 3. Click on submit. | Valid debit card details | Payment is processed successfully
TC_007 | Debit Card Payment | Invalid Debit Card Number | 1. Navigate to payment page. 2. Enter invalid debit card number. 3. Click on submit. | Invalid debit card number | Error message: "Invalid card number"
TC_008 | Debit Card Payment | Expired Debit Card | 1. Navigate to payment page. 2. Enter expired debit card details. 3. Click on submit. | Expired debit card details | Error message: "Card expired"
TC_009 | Debit Card Payment | Incorrect CVV | 1. Navigate to payment page. 2. Enter valid debit card details with incorrect CVV. 3. Click on submit. | Valid debit card details with incorrect CVV | Error message: "Incorrect CVV"
TC_010 | Debit Card Payment | Missing Expiration Date | 1. Navigate to payment page. 2. Enter debit card details without expiration date. 3. Click on submit. | Debit card details without expiration date | Error message: "Expiration date required"
You can continue adding more test cases in a similar format, with each row representing a unique test